|  | +34 674 993 637 hello@AOHospitalityAdvisors.com www.AOHospitalityAdvisors.com |
| --- | --- |

Dear Dean and Osama, A&H Hospitality Advisors

Thank you for the continued conversations on building a tech-enabled commercial performance hub for A&H clients. Below is a working draft collaboration framework for discussion — not a binding agreement — reflecting our alignment calls on 7 July and 16 July 2026. Executive Summary AO Hospitality Advisors proposes to subcontract to A&H Hospitality Advisors to design, build, and operate a commercial performance hub for A&H hotel clients, starting with one incubation property (current owner-operated Courtyard mandate). Goal: give owners and A&H advisors a single, trusted view of the KPIs that matter for commercial decisions — without A&H becoming a software company. Dashboard #1 (agreed direction, 16 July): Actuals · Budget · Forecast by segment — with segmentation + channel as the foundation. Pace is intentionally not the first dashboard: a single pace snapshot is weak until history accumulates; ABF by segment is more static and usable sooner. Dealality (AO’s deal-flow platform) remains out of scope for this engagement. The commercial hub must stand alone — clear costs, portable data/config — under the A&H brand unless A&H decides otherwise. Engagement Objectives • Establish a scalable data factory (ingest → clean → standardize → dashboard) using standardized upload first. • Deliver Dashboard #1: Actuals · Budget · Forecast by segment (with channel / direct vs indirect where available). • Define ownership, hosting, EU compliance, and commercial terms so both parties can scale to additional properties without rework. • Keep Phase 1 narrow; add pace, overlays, and Stairway-class snapshot history only after the foundation is live. Proposed Commercial Structure A&H = prime contractor to the hotel owner. AO = subcontractor to A&H, working under the A&H flag. • Contracting: A&H ↔ Client (MSA/SOW); A&H ↔ AO (subcontractor agreement + SOW per phase). • Branding (near-term default): A&H Hospitality Advisors on the commercial / performance hub. No Dealality branding on this deliverable. • Invoicing: A&H invoices the client; A&H pays AO per subcontract milestones. • Entity: AO = A-O entity (US); A&H = UK entity. Ownership Summary There is no single owner of “the dashboard.” Ownership splits across three layers — by design: • A&H owns the client — relationship, advisory, invoicing. • The hotel owner owns their data — actuals, forecasts, PMS exports, etc. • AO owns the platform — data factory, parsers, reusable UI shell, and code. A&H receives a non-exclusive license to deploy for A&H clients during the partnership. • The configured dashboard instance is a licensed deliverable for the A&H mandate — not a software product the owner buys outright. In one line: A&H owns the client · the owner owns the data · AO owns the technology · the client licenses the running instance. If A&H and AO Part Ways • Existing dashboards for active A&H mandates may keep running under a maintenance arrangement (AO retainer or agreed handover). • AO platform source code is not handed over by default; A&H may keep a maintenance license/retainer or freeze the deployment as-is. • Platform buyout is a separate commercial conversation, not included in build fees. • On exit, A&H receives a handover package: runbook, source map, and export of the client’s own data and configuration values (not AO source code). Guiding Principles • One dashboard, phased — under-promise, over-deliver. • Foundation before pace — segmentation (+ channel) → ABF by segment → then pace / overlays. • Data factory first — standardized upload short-term; live PMS integrations later. • Client-defined rules — segmentation, fiscal calendar, mapping library with an Other catchall. • Stand-alone platform — not mixed into Dealality; portable enough for another operator later. • EU-first compliance — design for EU GDPR; EU AI Act only when AI features are introduced (MVP is rules/code-based). Scope of Work Phase 0 — Discovery & Signed Wireframe (fixed fee) Objective: Lock Dashboard #1 = Actuals · Budget · Forecast by segment; complete source map, segmentation/channel rules, and success criteria before build. • Data & source inventory including 2–3 real sample files (A&H leads; AO documents). • Segmentation dictionary + channel dimension (direct / indirect / other) + YoY mapping rules. • Code/keyword → segment mapping library with Other catchall. • Fiscal calendar & budget/forecast input rules (entered once, used everywhere). • Clickable wireframe / mockup sign-off for ABF-by-segment. • Hosting region + estimated annual infra cost (EU-first). • Phase 1 scope, timeline, and single fixed price. Exit criteria: written sign-off on wireframe + source map + mapping library outline + Phase 1 SOW. Indicative planning range (not a quote): USD $3,000–$8,000. Phase 1 — MVP: Data Factory + Dashboard #1 (fixed fee — quoted after Phase 0) Objective: one working Actuals · Budget · Forecast by segment dashboard on the incubation hotel, with channel visibility where data allows, fed by standardized upload, hosted EU-compliant with secure A&H-branded logins. • Data factory for agreed sources only: validation, segment + channel mapping, refresh log, missed-upload alerts. • Core inputs: budget once; forecast once (transient vs group as required); segmentation config. • Commentary with audit trail; rules-based owner narrative (LLM optional in Phase 2+). • Handover runbook: who uploads what, when; how to refresh. Out of scope for MVP unless added by change order: full booking pace workspace; Stairway-class multi-year daily snapshot history; live PMS/RMS APIs; displacement calculator; portfolio roll-up; AI/LLM; additional dashboards; replacing Stairway as RMS. Acceptance criteria (all required): real-file ingest; segment + channel reconciliation; wireframe match; budget/forecast inputs; commentary; narrative; logins + A&H branding; runbook walkthrough. Indicative planning range (replaced by fixed quote after Phase 0): USD $15,000–$40,000. Phase 2 — Enhancements & Overlays (quoted per item / retainer) After the ABF foundation is live: booking pace; forecast accuracy; pace + forecast + comp overlays; market/comp views; LLM narrative (with EU AI Act review); portfolio; alerting; closer-to-live integrations. Indicative retainer: USD $2,000–$6,000/month AO subcontract (includes refresh monitoring, hosting, up to 4 hours/month light tweaks, monthly check-in). New sources, new dashboards, methodology changes, and APIs are change orders. Phase 3 — Additional Properties Per-property onboarding from a rate card after Phase 1 (typically lower than MVP because the factory exists). Ready-to-push checklist: source map, segmentation config, A&H training, UAT, support model. Longer Horizon — Stairway-Class Capability (Not Phase 1) Context (16 July): incubation owner currently uses Stairway (~€5,000/month). Contract renews September 2026 for another year; A&H has told the owner they are not ready to replace Stairway now. Realistic replace window: ~September 2027, preferably with more than one client sharing platform cost. Replacing Stairway also implies A&H operational RMS capacity (e.g. revenue manager) — advisory/ops, not only software. MVP does not commit to Stairway replacement. Phase 1 builds the scalable kit of parts so history/pace layers can be added without throwing away the foundation. Data Architecture (Direction) Short-term: upload / agreed extracts → data factory (validate, segment map library, channel map) → standard DB (actuals, budget, forecast, segment, channel; pace later) → dashboard layer (ABF by segment + commentary). • Segment = selling/marketing pattern (client-defined; brands/RMS vendors often disagree). • Channel = how the booking arrived (direct vs indirect); owner-critical for “value of the deal.” • Both dimensions must reconcile to the same totals; include an Other catchall. Pricing Model Recommendation Prefer a clean first step: fixed fee + fixed timeline + signed deliverable for Phase 0/1. Revisit percentage alignment after the first deliverable works. • Phase 0: always fixed. • Phase 1: fixed quote after Phase 0 (one number, not a range). • Phase 2: fixed monthly retainer. • Phase 3: fixed per-property rate card. Optional later alternative: 25–35% of A&H’s client implementation fee with floor and ceiling — only if A&H shares client pricing transparently. What A&H charges the hotel owner is entirely A&H’s decision. Ongoing hosting/database for a single-property MVP is typically low hundreds to low thousands USD per year (itemize in Phase 0). Proposed Payment Structure (AO ↔ A&H) • Currency: USD invoiced by AO to A&H. • Phase 0: 50% on SOW signature · 50% on delivery of signed wireframe + source map + Phase 1 quote. • Phase 1: 30% on SOW signature · 40% on data factory UAT · 30% on dashboard acceptance. • Retainer: monthly in advance; 30-day notice to pause or cancel. • Payment terms: Net 15 (negotiable to Net 30). Work pauses after 15 days overdue. • No travel/expenses unless pre-approved in writing. Operating Models After MVP • A — Handoff: build complete; hotel/A&H uploads; AO on call for break/fix or enhancements. • B — Managed refresh: A&H or AO processes weekly feeds into the factory. • C — AO maintain & manage: ongoing ops under retainer; enhancements quoted separately. First engagement should prove Model A or B before assuming C. Hosting, Branding & Stand-Alone Stack • Storage/platform has a clear owner (default: AO-managed infra under A&H branding). • Stand-alone environment — not shared cost pools with Dealality. • Login URL, page title, and notifications = A&H Hospitality Advisors. • Design for portability: export of client data + config. Security, Confidentiality & EU-First Data Protection A&H’s near-term commercial clients include EU properties — design to the stricter EU bar. • AO is processor to A&H; EU hosting default for EU client data. • Subcontract includes processor/DPA-style terms; subprocessors listed and approved. • MVP is rules/code-based; EU AI Act review before any LLM/AI feature. • AO cleans and presents data but is not the system of record; A&H/owner remain responsible for business decisions. • AO liability cap: fees paid under the applicable SOW (confirm with counsel). Governance • Biweekly steering during build; monthly in retainer. • Written change requests with time/cost impact; A&H gatekeeps client scope. • Points of contact: A&H commercial (Dean / Osama); AO technical (Joan). Project Team Joan Dejarden — Principal / Technical Lead (AO): Hospitality strategy and technology delivery; responsible for architecture, data factory, hosting, UI, and runbooks under the A&H flag. A&H Hospitality Advisors (Dean Auburn & Osama): Commercial subject-matter experts, client relationship, KPI/segmentation definition, and owner-facing advisory. Delivery Risks & Assumptions Shared openly so A&H and AO plan Phase 0/1 with eyes open. These are management risks, not reasons to pause — they define what must be true for the fixed-fee path to work. Assumptions (Phase 1 depends on these) • Phase 1 starts only after Phase 0 delivers 2–3 real sample export files and a signed source map. • Dashboard #1 remains Actuals · Budget · Forecast by segment (+ channel only where data is confirmed available). • Short-term ingest is standardized upload / agreed extracts, not live PMS/RMS APIs. • A&H owns the segmentation + channel dictionary; AO implements the signed mapping library (including Other). • The hub is a stand-alone stack (not mixed into Dealality), with EU hosting where required. • MVP is rules/code-based (no LLM/AI until a separate EU AI Act review). • Replacing Stairway / daily multi-year snapshot history is out of Phase 1 (~Sep 2027 horizon). • A&H remains client-facing; AO does not provide on-property revenue-management staffing. Delivery risks & mitigations Data quality / messiness unknown: Until real files are seen, effort and the Phase 1 fixed price are estimates. Mitigation: Phase 0 includes sample files; Phase 1 is one fixed quote only after file review. Late or unusable files → timeline flex or Phase 0 kill. Scope creep into pace / Stairway-class: Pace and daily snapshot history are a different product class. Mitigation: written SOW boundaries; pace/overlays = Phase 2+; Stairway replacement = separate later SOW. Segmentation / channel disagreement: Brand, Stairway, and owner definitions often conflict. Mitigation: A&H signs the dictionary; AO implements only the signed map; reconciliation + Other catchall required. Direct/indirect not available at hotel level: Channel views are owner-critical but access is unconfirmed. Mitigation: confirm in Phase 0; if unavailable, ship ABF-by-segment without channel (or limited proxy) and quote channel as a change order. Client / A&H data latency: Waiting on extracts looks like AO delay. Mitigation: day-for-day timeline extension; pause rights after extended delay. EU hosting / GDPR / future AI: Wrong region or premature AI creates compliance risk. Mitigation: EU host in Phase 0; DPA-style terms; AI only after joint EU AI Act review. Operating-model mismatch: If A&H expects AO to run Stairway-like RMS ops, that is staffing + advisory — not Phase 1 software. Mitigation: Phase 1 = build + handoff or light refresh (Models A/B); Model C only under explicit retainer; RMS ops remains A&H. Planning ranges read as quotes: USD $15k–$40k can be treated as a firm offer before discovery. Mitigation: all Phase 1 ranges are planning anchors only; the binding number is the post–Phase 0 fixed quote. Solo delivery / calendar risk: Lean delivery and AI-assisted coding do not remove QA, demos, or dependency waits. Mitigation: buffer calendar time; under-promise weeks; change control for new widgets/sources. Brand / PMS system changes: Platform moves can change feed formats mid-engagement. Mitigation: adaptable parsers; format changes after Phase 0 = change order. What “done” for Phase 1 does not mean • Not a Stairway replacement • Not full booking-pace history • Not live PMS integration • Not AI-generated commercial advice • Not AO owning the client relationship or owner RM decisions Illustrative Commercial Summary (Planning Anchors Only) Phase 0 Discovery + signed ABF wireframe — Fixed — USD $3k–$8k Phase 1 Factory + ABF-by-segment dashboard (1 hotel) — Fixed quote after Phase 0 — USD $15k–$40k planning range Phase 2 Pace / overlays / enhancements — Fixed monthly retainer + per-SOW — USD $2k–$6k/mo Phase 3 Additional properties — Fixed per property (rate card) — TBD after Phase 1 Later Stairway-class snapshot platform — Separate SOW — TBD; multi-client preferred These anchors are not binding quotes. Phase 1 becomes a single fixed price in the Phase 0 deliverable. Suggested Next Steps • Dean reviews this draft with Osama and mark up ownership, hosting, branding, and fixed-fee Phase 1. • Confirm Dashboard #1 = ABF by segment and any performance-test KPIs for v1. • Schedule a three-way regroup. • Kick off Phase 0 with 2–3 real sample export files from the incubation hotel. Interactive mockup (illustrative data): https://joandejarden-create.github.io/ah-commercial-performance-hub/ Conclusion We believe starting with Actuals · Budget · Forecast by segment — on a stand-alone, EU-ready stack under the A&H flag — is the cleanest path to a valuable first deliverable, while preserving the option to add pace and Stairway-class capability over the next year. This document is a working draft for discussion. I am happy to revise based on your and Osama’s comments and then convert agreed sections into a Phase 0 SOW. Please don’t hesitate to contact me directly at +34 674 993 637 or via email at hello@AOHospitalityAdvisors.com should you have any questions. I look forward to continuing the conversation. Best regards, Joan Dejarden AO Hospitality Advisors